## Sheet1
Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
Hallucination detector fails to flag unsupported numerical claims when context is empty. | Sprint 1 | Self | Functional / Logic | Added fallback check to return default penalty score if context is missing. | 2026-07-10 | Closed | Resolved in patch v1.0.1
ChromaDB vector store timeout when indexing large batch CSV uploads. | Sprint 2 | Self | Performance | Implemented batch chunking (50 items per batch) with async execution. | 2026-07-15 | Closed | Optimized retrieval speed
Chart.js dashboard canvas fails to resize correctly on dark mode toggle. | Sprint 3 | Self | UI / UX | Updated CSS flexbox wrappers and added explicit chart instance destroy methods. | 2026-07-21 | Closed | Fixed layout glitch
Gemini API rate limit error (429 Too Many Requests) during concurrent multi-agent execution. | Sprint 3 | Self | Integration | Added exponential backoff retry decorator to all Gemini client calls. | 2026-07-29 | Closed | Stabilized agent pool
CSV export button generates empty file if evaluation history is empty. | Sprint 4 | Self | Functional | Added client-side validation to disable export when dataset length is zero. | 2026-08-01 | Open | Resolved in patch v1.0.1
PDF report layout cuts off longer reasoning blocks from the Hallucination Detector. | Sprint 4 | Self | UI / PDF G | Done | 2026-08-05 | Open | Resolved in patch v1.0.1